W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | CONSTRUCTION | 180000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | RIGHT-OF-WAY | 30000
W-5712REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | REGION F |  | HSIP | RIGHT-OF-WAY | 30000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000 | FY 2023: 40000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000 | FY 2023: 240000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5712SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 12 | Gaston-Cleveland-Lincoln MPO, Greater Hickory MPO, Charlotte Regional TPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5712U | HIGHWAY | NC 150 | MILEPOST 19.3 TO GASTON COUNTY LINE AND FROM THE CLEVELAND COUNTY LINE TO MILEPOST 1.2. CONSTRUCT SAFETY IMPROVEMENTS. | 12 | Gaston-Cleveland-Lincoln MPO |  | REGION F |  | HSIP | CONSTRUCTION | 625000 | FY 2025: 625000
W-5713 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | COMPLETE |  |  |  |  | 6567000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | CONSTRUCTION | 180000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | CONSTRUCTION | 180000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 30000
W-5713DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 13 |  | HSIP | CONSTRUCTION | 180000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5713REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000 | FY 2023: 240000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5713SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 13 | High Country RPO, Foothills RPO, French Broad River MPO, Greater Hickory MPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000 | FY 2023: 40000
W-5714 | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS |  |  |  |  | 1499000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | CONSTRUCTION | 180000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | CONSTRUCTION | 180000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | CONSTRUCTION | 180000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714DIV | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | DIVISION 14 |  | HSIP | RIGHT-OF-WAY | 30000
W-5714E | HIGHWAY | US 64 | SR 1119 (SAPPHIRE POSTOFFICE ROAD) AT CHRYSLER CURVE NEAR SAPPHIRE. CONSTRUCT SAFETY IMPROVEMENTS. | 14 | Southwestern RPO |  | REGION G |  | HSIP | CONSTRUCTION | 975000 | FY 2024: 975000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000 | FY 2023: 30000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000 | FY 2023: 180000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | CONSTRUCTION | 180000
W-5714REG | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | REGION G |  | HSIP | RIGHT-OF-WAY | 30000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000 | FY 2023: 240000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000 | FY 2023: 40000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 40000
W-5714SW | HIGHWAY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | 14 | Southwestern RPO, French Broad River MPO, Foothills RPO, Land-of-Sky RPO | IN PROGRESS. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 240000
W-5715DIV | HIGHWAY | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | ENGINEERING | 9180000 | 1230000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 900000
W-5715REG | HIGHWAY | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | ENGINEERING | 9180000 | 1230000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 900000
W-5715SW | HIGHWAY | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | ENGINEERING | 12240000 | 1640000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 1200000
W-5716DIV | HIGHWAY | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | ENGINEERING | 26400000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 3300000
W-5716REG | HIGHWAY | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | ENGINEERING | 26400000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 1650000 | 3300000
W-5716SW | HIGHWAY | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | ENGINEERING | 35200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 4400000
W-5717DIV | HIGHWAY | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | ENGINEERING | 10200000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 1500000
W-5717REG | HIGHWAY | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | ENGINEERING | 10200000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 1500000
W-5717SW | HIGHWAY | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | ENGINEERING | 13600000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 2000000
W-5802A | HIGHWAY | SR 1493 | SR 1493 (LIVE OAK STREET) AT CAMPEN ROAD. REVISE TRAFFIC SIGNAL, INSTALL PEDESTRIAN CROSSING WITH SIGNAL HEADS, AND UPGRADE SIDEWALK. | 2 | Down East RPO | COMPLETED. | DIVISION 2 |  | HSIP | CONSTRUCTION | 38000
W-5802B | HIGHWAY | NC 58 | NC 58 (E. FORT MACON ROAD) AT BROOKS STREET. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | 2 | Down East RPO | COMPLETED. | REGION B |  | HSIP | CONSTRUCTION | 30000
W-5802C | HIGHWAY | NC 58 | NC 58 (E. FORT MACON ROAD) AT E. BOGUE SOUND DRIVE. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | 2 | Down East RPO | COMPLETED. | REGION B |  | HSIP | CONSTRUCTION | 30000
W-5802E | HIGHWAY | US 70, NC 55 | US 70 BETWEEN NUNN STREET AND SR 1605 (FRIENDLY ROAD) IN MOREHEAD CITY, AND NC 55 BETWEEN US 17 IN BRIDGETON AND SR 1210 (1ST STREET) IN BAYBORO. INSTALL 6 INCH LONG LIFE PAVEMENT MARKINGS. | 2 | Down East RPO | COMPLETED. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 865000
W-5803A | HIGHWAY | US 74 | US 74 (EASTWOOD ROAD) AT US 17 (MILITARY CUTOFF ROAD), AND US 74 (EASTWOOD ROAD) AT CAVALIER DRIVE IN WILMINGTON. UPGRADE PEDESTRIAN SIGNALS. | 3 | Wilmington Urban Area MPO |  | REGION B |  | HSIP | CONSTRUCTION | 42000 | FY 2023: 42000
W-5803B | HIGHWAY | US 17 | US 17 BETWEEN NEW HANOVER / PENDER COUNTY LINE AND MILE POST 19.3 IN ONSLOW COUNTY. INSTALL SHOULDER RUMBLE STRIPS. | 3 | Jacksonville Urban Area MPO, Wilmington Urban Area MPO, Cape Fear RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 438000 | FY 2023: 438000
W-5803C | HIGHWAY | US 17 BUSINESS | US 17 BUSINESS (MARINE BOULEVARD) AND SR 1402 (OLD BRIDGE STREET). UPGRADE TRAFFIC SIGNAL, PAVEMENT MARKINGS, AND IMPROVE SIGHT DISTANCE. | 3 | Jacksonville Urban Area MPO | UNDER CONSTRUCTION. | REGION B |  | HSIP | CONSTRUCTION | 85000 | FY 2023: 85000
W-5803D | HIGHWAY | NC 24 | NC 24 (WEST CORBETT AVENUE) AND SR 1512 (OLD HAMMOCKS ROAD). UPGRADE PEDESTRIAN SIGNALS. | 3 | Jacksonville Urban Area MPO | COMPLETED. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 17000
W-5803E | HIGHWAY | NC 53 | NC 53 (WESTERN BOULEVARD) AND CENTER STREET / LIBERTY DRIVE. UPGRADE TRAFFIC SIGNAL AND ADD ADDITIONAL SPEED LIMIT SIGNS. | 3 | Jacksonville Urban Area MPO | COMPLETED. | REGION B |  | HSIP | CONSTRUCTION | 57000
W-5804A | HIGHWAY | US 301 | US 301 AT NC 581. CONSTRUCT A REDUCED CONFLICT INTERSECTION WITH TRUCK BULB-OUTS AT THE ADJACENT U-TURN POINTS. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | RIGHT-OF-WAY | 100000
W-5804A | HIGHWAY | US 301 | US 301 AT NC 581. CONSTRUCT A REDUCED CONFLICT INTERSECTION WITH TRUCK BULB-OUTS AT THE ADJACENT U-TURN POINTS. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 2334000
W-5804B | HIGHWAY | NC 43 | NC 43 AT SR 1500 (SWIFT CREEK SCHOOL ROAD). REALIGN INTERSECTION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | RIGHT-OF-WAY | 45000 | FY 2023: 45000
W-5804B | HIGHWAY | NC 43 | NC 43 AT SR 1500 (SWIFT CREEK SCHOOL ROAD). REALIGN INTERSECTION. | 4 | Upper Coastal Plain RPO | UNDER CONSTRUCTION. | REGION A |  | HSIP | CONSTRUCTION | 651000 | FY 2023: 7000; FY 2024: 644000
W-5805A | HIGHWAY | NC 42 | SR 1101 (PINEY GROVE - WILBON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 5 | Capital Area MPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 235000 | FY 2023: 235000
W-5805A | HIGHWAY | NC 42 | SR 1101 (PINEY GROVE - WILBON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | 5 | Capital Area MPO |  | REGION C |  | HSIP | CONSTRUCTION | 725000 | FY 2024: 239000; FY 2025: 486000
W-5805C | HIGHWAY | SR 1820 (LEAD MINE ROAD) | SR 1827 (LYNN ROAD) INTERSECTION IN RALEIGH. CONSTRUCT PEDESTRIAN REFUGE ISLANDS, AND REVISE CURB RAMPS, CROSSWALKS, AND OTHER PAVEMENT MARKINGS. | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | HSIP | CONSTRUCTION | 292000 | FY 2023: 288000
W-5805D | HIGHWAY | NC 42 | BRIDGE 910023 OVER MIDDLE CREEK. INSTALL GUARDRAIL. | 5 | Capital Area MPO | UNDER CONSTRUCTION | REGION C |  | HSIP | CONSTRUCTION | 184000 | FY 2023: 172000
W-5805E | HIGHWAY | NC 98 | SR 2057 / SR 4465 (MOORES POND ROAD) | 5 | Capital Area MPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 100000 | FY 2023: 100000
W-5805E | HIGHWAY | NC 98 | SR 2057 / SR 4465 (MOORES POND ROAD) | 5 | Capital Area MPO |  | REGION C |  | HSIP | CONSTRUCTION | 1230000 | FY 2024: 12000; FY 2025: 1218000
W-5805F | HIGHWAY | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS | 5 | Capital Area MPO, Kerr-Tar RPO | UNDER CONSTRUCTION | DIVISION 5 |  | HSIP | CONSTRUCTION | 2553000 | FY 2023: 256000
W-5805G | HIGHWAY | US 1 | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | 5 | Kerr-Tar RPO |  | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 45000 | FY 2023: 45000
W-5805G | HIGHWAY | US 1 | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED REDUCED CONFLICT INTERSECTION. | 5 | Kerr-Tar RPO |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 955000 | FY 2023: 10000; FY 2024: 945000
W-5805H | HIGHWAY | SR 1004 (GARNER ROAD); TIMBER DRIVE EAST | SR 2539 (YEARGAN ROAD), SR 2564 (CREECH ROAD), AND SHENSTONE BOULEVARD INTERSECTIONS IN GARNER. UPGRADE TRAFFIC SIGNALS | 5 | Capital Area MPO | UNDER CONSTRUCTION | DIVISION 5 |  | HSIP | CONSTRUCTION | 75000
W-5806A | HIGHWAY | NC 11 | NC 11 AT SR 1740 (OLD LAKE ROAD). CONSTRUCT ROUNDABOUT. | 6 | Cape Fear RPO |  | REGION C |  | HSIP | RIGHT-OF-WAY | 85000 | FY 2024: 85000
W-5806A | HIGHWAY | NC 11 | NC 11 AT SR 1740 (OLD LAKE ROAD). CONSTRUCT ROUNDABOUT. | 6 | Cape Fear RPO |  | REGION C |  | HSIP | CONSTRUCTION | 1342000 | FY 2025: 630000; FY 2026: 712000
W-5806B | HIGHWAY | SR 1117, SR 3242, SR 1615 | SR 1117 (NURSERY ROAD) FROM NC 27 TO SR 3242 (OVERHILLS ROAD). SR 3242 (OVERHILLS ROAD) FROM NC 24/87 TO SR 1117 (NURSERY ROAD). SR 1121 (RAY ROAD) FROM SR 1117 (NURSERY ROAD) TO SR 3242 (OVERHILLS ROAD). WIDEN CURVES AND INSTALL RUMBLE STRIPS. | 6 | Fayetteville Area MPO, Mid-Carolina RPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 400000 | FY 2023: 396000
W-5806C | HIGHWAY | SR 1615 (ROSEHILL ROAD) | SR 1615 (ROSEHILL ROAD) AT TAMARACK DRIVE AND SR 1615 (ROSEHILL ROAD) AT LANDAU ROAD. CONSTRUCT MINI-ROUNDABOUTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | CONSTRUCTION | 1850000 | FY 2023: 1850000
W-5806C | HIGHWAY | SR 1615 (ROSEHILL ROAD) | SR 1615 (ROSEHILL ROAD) AT TAMARACK DRIVE AND SR 1615 (ROSEHILL ROAD) AT LANDAU ROAD. CONSTRUCT MINI-ROUNDABOUTS. | 6 | Fayetteville Area MPO | UNDER CONSTRUCTION. | DIVISION 6 |  | HSIP | RIGHT-OF-WAY | 75000
W-5806D | HIGHWAY | NC 27, SR 1581 | NC 27 AT SR 1581 (BAILEY'S CROSSROADS) / SR 1705 (FAIRGROUND). REALIGNMENT / INTERSECTION IMPROVEMENTS. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | RIGHT-OF-WAY | 100000
W-5806D | HIGHWAY | NC 27, SR 1581 | NC 27 AT SR 1581 (BAILEY'S CROSSROADS) / SR 1705 (FAIRGROUND). REALIGNMENT / INTERSECTION IMPROVEMENTS. | 6 | Mid-Carolina RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | CONSTRUCTION | 586000 | FY 2023: 580000
W-5806E | HIGHWAY | NC 41 (MARTIN LUTHER KING JR DRIVE) | NC 41 (MARTIN LUTHER KING JR DRIVE) AT NC 72 (WEST SECOND STREET) AND SR 1599 (MARTIN LUTHER KING JR DRIVE). CONSTRUCT SIGNALIZED PEDESTRIAN CROSSINGS. | 6 | Lumber River RPO | UNDER CONSTRUCTION. | REGION C |  | HSIP | CONSTRUCTION | 315000 | FY 2023: 312000
W-5807A | HIGHWAY | US 220 EASTBOUND | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | HSIP | RIGHT-OF-WAY | 150000 | FY 2023: 150000
W-5807A | HIGHWAY | US 220 EASTBOUND | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | 7 | Greensboro Urban Area MPO | RIGHT-OF-WAY IN PROGRESS | REGION D |  | HSIP | CONSTRUCTION | 280000 | FY 2023: 3000; FY 2024: 277000
W-5807B | HIGHWAY | SR 1301 (BOONE STATION DRIVE) | SR 1301 (ST. MARKS CHURCH ROAD) / JAVA LANE AND GLIDWELL DRIVE / TIKI LANE IN BURLINGTON. INSTALL PEDESTRIAN SIGNALS AND CURB RAMPS, AND REVISE PAVEMENT MARKINGS. | 7 | Burlington-Graham MPO |  | DIVISION 7 |  | HSIP | CONSTRUCTION | 75000 | FY 2023: 75000
W-5808B | HIGHWAY | US 421 | NC 902 INTERSECTION. CONVERT EXISTING SIGNALIZED INTERSECTION TO A REDUCED CONFLICT INTERSECTION. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | RIGHT-OF-WAY | 100000
W-5808B | HIGHWAY | US 421 | NC 902 INTERSECTION. CONVERT EXISTING SIGNALIZED INTERSECTION TO A REDUCED CONFLICT INTERSECTION. | 8 | Triangle Area RPO | RIGHT-OF-WAY IN PROGRESS | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 736000 | FY 2024: 334000; FY 2025: 402000
W-5808C | HIGHWAY | SR 2055 (NORTH POPLAR STREET) | WEST MAPLE AVENUE INTERSECTION IN ABERDEEN. INSTALL ALL-WAY STOP. | 8 | Triangle Area RPO | UNDER CONSTRUCTION. | DIVISION 8 |  | HSIP | RIGHT-OF-WAY | 2000
W-5808C | HIGHWAY | SR 2055 (NORTH POPLAR STREET) | WEST MAPLE AVENUE INTERSECTION IN ABERDEEN. INSTALL ALL-WAY STOP. | 8 | Triangle Area RPO | UNDER CONSTRUCTION. | DIVISION 8 |  | HSIP | CONSTRUCTION | 15000
W-5809A | HIGHWAY | NC 109 | DENTON NORTHERN MUNICIPAL BOUNDARY TO SR 2067 (LAMBETH ROAD), AND SR 1798 (OLD GREENSBORO ROAD) / SR 1756 (WEST LEXINGTON AVENUE EXTENSION) TO SR 1711 (GUMTREE ROAD). INSTALL RUMBLE STRIPS AND LONG-LIFE PAVEMENT MARKINGS. | 9 | High Point Urban Area MPO | UNDER CONSTRUCTION | REGION D |  | HSIP | CONSTRUCTION | 1100000
W-5813A | HIGHWAY | US 25 | US 25 (MCDOWELL STREET) AT DOCTOR'S DRIVE/ASHEVILLE HIGH SCHOOL ENTRANCE. INSTALL PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 64000
W-5813B | HIGHWAY | VARIOUS | VARIOUS SR LOCATIONS. INSTALL LONG LIFE PAVEMENT MARKINGS. | 13 | Foothills RPO, Greater Hickory MPO, High Country RPO | UNDER CONSTRUCTION. | DIVISION 13 |  | HSIP | CONSTRUCTION | 1600000 | FY 2023: 1584000
W-5813C | HIGHWAY | SR 1332 | SR 1332 (NORTH LOUISIANA AVENUE) AT SR 1338 (EMMA ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, SIDEWALK AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | HSIP | RIGHT-OF-WAY | 2000
W-5813C | HIGHWAY | SR 1332 | SR 1332 (NORTH LOUISIANA AVENUE) AT SR 1338 (EMMA ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, SIDEWALK AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | DIVISION 13 |  | HSIP | CONSTRUCTION | 95000 | FY 2023: 95000
W-5813D | HIGHWAY | US 25 | ALL SOULS CRESCENT AND US 25 ALT (LODGE STREET) INTERSECTIONS. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | 13 | French Broad River MPO |  | REGION G |  | HSIP | CONSTRUCTION | 96000 | FY 2023: 1000; FY 2024: 95000
W-5813E | HIGHWAY | US 19-23-74 ALT | US 19-23-74 ALT (PATTON AVENUE) AT US 19-23 BUS (HAYWOOD ROAD)/SR 1319 (JOHNSTON ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 115000 | FY 2023: 115000
W-5813F | HIGHWAY | US 19-23-74 ALT | US 19-23-74 ALT (SMOKEY PARK HIGHWAY) AT OLD HAYWOOD ROAD. INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 70000 | FY 2023: 70000
W-5813G | HIGHWAY | US 70; US 74 ALT | (1) US 70 (TUNNEL ROAD) AT OLD CHUNNS COVE ROAD, (2) US 74 ALT (S. TUNNEL ROAD) AT MAIN MALL ENTRANCE (EAST LEG), (3) US 74 ALT (S. TUNNEL ROAD) AT LOWER MALL ENTRANCE. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | 13 | French Broad River MPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 135000 | FY 2023: 134000
W-5813H | HIGHWAY | NC 197 | NC 197 FROM SR 1338 TO THE MITCHELL COUNTY LINE, NEAR GREEN MOUNTAIN. INSTALL SHOULDER GUARDRAIL. | 13 | High Country RPO | COMPLETE | REGION G |  | HSIP | CONSTRUCTION | 474000
W-5813I | HIGHWAY | SR 2806 | SR 2806 (GARREN CREEK ROAD) FROM SR 2815 TO SR 2786, NEAR FAIRVIEW. INSTALL SHOULDER GUARDRAIL. | 13 | Land-of-Sky RPO | COMPLETE | DIVISION 13 |  | HSIP | CONSTRUCTION | 460000
W-5813J | HIGHWAY | US 221 | (1) US 221 IN RUTHERFORD COUNTY FROM US 64 TO THE MCDOWELL COUNTY LINE. (2) US 221 IN MCDOWELL COUNTY ROM THE RUTHERFOD COUNTY LINE TO I-40. INSTALL SINUSIODAL CENTERLINE RUMBLESTRIPES WITH LONG-LIFE PAVEMENT MARKINGS. | 13 | Foothills RPO | UNDER CONSTRUCTION. | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 501000 | FY 2023: 496000
W-5814A | HIGHWAY | US 276 | CONSTRUCT LEFT TURN LANE 0.3 MILES SOUTH OF SR 1326 (BOB BOYD ROAD). | 14 | Land-of-Sky RPO | UNDER CONSTRUCTION. | REGION G |  | HSIP | CONSTRUCTION | 380000
W-5814B | HIGHWAY | US 74 WB | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | 14 | Foothills RPO | COMPLETE | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 199000
W-5814C | HIGHWAY | US 74 EB | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | 14 | Foothills RPO | COMPLETE | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 179000
W-9999DIV | HIGHWAY | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | HSIP | CONSTRUCTION | 45163000 | FY 2023: 4903000
W-9999REG | HIGHWAY | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | 99 | STATEWIDE PROJECT |  | REGION SW |  | HSIP | CONSTRUCTION | 55935000 | FY 2023: 15750000
W-9999SW | HIGHWAY | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | 99 | STATEWIDE PROJECT |  | STATEWIDE MOBILITY |  | HSIP | CONSTRUCTION | 74580000 | FY 2023: 21000000
X-0002 | HIGHWAY | I-295 (FAYETTEVILLE OUTER LOOP) | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO I-95. FREEWAY ON NEW LOCATION WITH STRUCTURE OVER THE CAPE FEAR RIVER. | 6 | Fayetteville Area MPO | [5 empty] | 320483000
Y-4805F | RAIL | FAYETTEVILLE STREET (SR 2513) | FAYETTEVILLE STREET AND THE CAROLINA COASTAL RAILWAY TRACKS CROSSING CLOSURE IN KNIGHTDALE. | 5 | Capital Area MPO |  | DIVISION 5 |  | RR | CONSTRUCTION | 1600000 | FY 2025: 1600000
Y-4807B | RAIL | LOWDERMILK STREET SYKES AVENUE | PINE STREET CROSSING CLOSURE AND LOWDERMILK STREET / SYKES AVENUE REALIGNMENT IN GREENSBORO. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  | RR | CONSTRUCTION | 5000000 | FY 2023: 50000; FY 2024: 4477000; FY 2025: 473000
Y-4807B | RAIL | LOWDERMILK STREET SYKES AVENUE | PINE STREET CROSSING CLOSURE AND LOWDERMILK STREET / SYKES AVENUE REALIGNMENT IN GREENSBORO. | 7 | Greensboro Urban Area MPO |  | DIVISION 7 |  |  |  | 2430000
Y-4810K | RAIL | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | STATEWIDE MOBILITY |  |  |  | 2800000
Y-4810K | RAIL | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | STATEWIDE MOBILITY |  | O | CONSTRUCTION | 450000 | FY 2023: 111000; FY 2024: 233000; FY 2025: 106000
Y-4810K | RAIL | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. | 10 | Cabarrus-Rowan MPO | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN | STATEWIDE MOBILITY |  | T | CONSTRUCTION | 18720000 | FY 2023: 4632000; FY 2024: 9675000; FY 2025: 4413000
Y-5500 | RAIL | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 1944000
Y-5500 | RAIL | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  | RR | CONSTRUCTION | 7560000 | FY 2023: 2500000
Y-5500 | RAIL | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  | RR | RIGHT-OF-WAY | 1500000 | FY 2023: 500000
Z-5400 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 28841000
Z-5700 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | 99 | STATEWIDE PROJECT | IN PROGRESS | DIVISION SW |  |  |  | 16738000
Z-5800 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | RR | CONSTRUCTION | 3280000
Z-5800 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | RR | RIGHT-OF-WAY | 500000
Z-9999 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS - UNPROGRAMMED BALANCE. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | RR | RIGHT-OF-WAY | 500000 | FY 2023: 500000
Z-9999 | RAIL | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS - UNPROGRAMMED BALANCE. | 99 | STATEWIDE PROJECT |  | DIVISION SW |  | RR | CONSTRUCTION | 3000000 | FY 2023: 3000000

## Fund Sources
Fund Source | Fund Type | Description | Subject to STI
3037 | Federal | Job Assistance and Reverse Commute | No
5303 | Federal | Metropolitan Planning (FMPL) | No
5305 | Federal | FTA Discretionary Grant Funds | No
5307 | Federal | Urbanized Area Formula Program (FUZ) | No
5309 | Federal | Capital Program - Bus Earmark (FBUS) | No
5310 | Federal | Elderly and Persons with Disability (FEPD) | No
5311 | Federal | Non Urbanised Area Formula Program (FNU) | No
5312 | Federal | FUZ 5312 | No
5316 | Federal | Job Assistance And Reverse Commute (JARC) | No
5317 | Federal | New Freedom Program | No
5337 | Federal | Urbanized Area Formula Program (FUZ) | No
5339 | Federal | Capital Program - Bus Earmark (FBUS) | No
5339(b) | Federal | Capital Program - Bus Earmark (FBUS) - Discretionary Grant | No
ADHS | Federal | Appalachian Development Highway System | No
ADHSL | Federal | Appalachian Development Highway System (Local Access Roads) | No
ADTAP | Federal | Appalachian Development portion of 5311 - Non Urbanised Area Formula Program (FNU) | No
ARP | Federal | American Rescue Plan | No
BA | State | Bonus Allocation | No
BFP | Federal | Federal Bridge Improvement Program - Formula | Yes
BFPOFF | Federal | Federal Bridge Improvement Program - Formula (Off System) | Yes
BG | Federal | Surface Transportation Block Grant Program (Uncategorized) | Yes
BG5200 | Federal | Surface Transportation Block Grant Program (5K - 200K) | Yes
BGANY | Federal | Surface Transportation Block Grant Program (Any Area) | Yes
BGBA | Federal | Surface Transportation Block Grant Program (Bonus Allocation) | No
BGDA | Federal | Surface Transportation Block Grant Program (Direct Attributable) | Yes
BGDACV | Federal | COVID Relief Funds | Yes
BGIM | Federal | Surface Transportation Block Grant Program (Interstate Maintenance) | Yes
BGLT5 | Federal | Surface Transportation Block Grant Program (Less than 5K) | Yes
BGOFF | Federal | Surface Transportation Block Grant Program (Off System) | Yes
BOND R | Other | Revenue Bond | No
BRGI | Federal | Bridge Inspection | Yes
CARES | Federal | CARES Act Funding | No
CMAQ | Federal | Congestion Mitigation | No
CRP550 | Federal | Carbon Reduction Program - (5K - 50K) | No
CRPANY | Federal | Carbon Reduction Program - Any Area | No
CRPDA | Federal | Carbon Reduction Program - Direct Attributable (All MPOs) | No
CRPLT5 | Federal | Carbon Reduction Program - (Less than 5K) | No
DOD | Federal | Department of Defense | No
DP | Federal | Discretionary or Demonstration | No
ER | Federal | Emergency Relief | No
ERFO | Federal | Emergency Relief for Federally Owned Roads | No
FED | Federal | Unidentified Federal Funding | No
FEDT | Federal | Undesignated Federal Transit Funding | No
FF | Federal | FEDERAL FERRY | Yes
FLAP | Federal | Federal Lands Access Program (Park Roads) | No
FLPF | Federal | Federal Lands Program (Forest Roads) | No
FLTP | Federal | Federal Lands Transportation Program | No
FMOD | Federal | Fixed Guideway Modifications | Yes
FSPR | Federal | State Planning and Research | No
FTTP | Federal | Federal Tribal Transportation Program | No
FUZ | Federal | Capital Program - Bus Earmark (5309) | No
HF | State | Highway Fund | No
HFB | State | Highway Fund Bridge Replacement Program | Yes
HIB | Federal | Highway Infrastructure Bridge Replacement | Yes
HP | Federal | High Priority | Yes
HRRR | Federal | High Risk Rural Roads | Yes
HSIP | Federal | HIGHWAY SAFETY IMPROVEMENT PROGRAM | Yes
L | Other | Local | No
NEVI | Federal | National Electric Vehicle Infrasructure Program Funds | Yes
NHFP | Federal | National Highway Freight Program | Yes
NHP | Federal | National Highway Performance Program | Yes
NHPB | Federal | National Highway Performance Program(Bridge) | Yes
NHPBA | Federal | National Highway Performance Program(Bonus Allocation) | No
NHPIM | Federal | National Highway Performance Program (Interstate Maintenance) | Yes
NRT | Federal | National Recreation Trails | Yes
O | Other | Local, Non Federal or State Funds | No
PROTCT | Federal | PROTECT Formula Program (Promoting Resilient Operations…) | Yes
RR | Federal | Rail-Highway Safety | Yes
RTAP | Federal | Rural Transit Assistance Program | No
S | State | State | No
S(M) | State | State Match for STP-DA or Garvee Projects | Yes
S(M)BA | State | State Match for Bonus Allocation Projects using Federal funds | No
SBG | Federal | Scenic Byway Grant | Yes
SF | State | Ferries | Yes
SMAP | State | Operating Assistance and State Maintenance | No
SRTS | Federal | Safe Roads to School | Yes
SSO | Federal | Safety System Oversight | No
STHSR | Federal | Stimulus High Speed Rail | No
T | State | Highway Trust Funds | Yes
T(DA) | State | Highway Trust Funds - Fund Swaps for DA Projects | Yes
TA | Federal | Transportation Alternatives Program (Uncategorized) | Yes
TA5200 | Federal | Transportation Alternatives Program (5K - 200K) | Yes
TAANY | Federal | Transportation Alternatives Program (Any Area) | Yes
TADA | Federal | Transportation Alternatives Program (Direct Attributable) | Yes
TALT5 | Federal | Transportation Alternatives Program (Less than 5K) | Yes
TAP | Federal | Transportation Alternatives Program (Uncategorized) | Yes
TAPDA | Federal | Transportation Alternatives Program (Direct Attributable) | Yes
VRU | Federal | Vulnerable Road User | Yes